## Base Data (hidden)
S.No | Group | Description | Viaduct | Station | Traction | Rolling Stock | Telecom | Depot | Signalling | Track | E&M
1 |  | Submission of detailed construction programme & methodology | Mayur
1.1 |  | Construction Programme
1.2 |  | Construction Methodology
2 |  | Submission of detailed design & GFCDs of open/raft/footing/pile foundations and construction incuding pile cap, pier cap, bearings, shear keys, seismic restrainers, hold down devices if required etc complete. | Mayur
2.1 |  | Pile/open Foundation | Mayur
2.2 |  | Pilecap & Pier | Mayur
2.3 |  | Pier Cap | Mayur
2.4 |  | Pier Arm | Mayur
3 |  | Submission of detail design and GFCDs of super structure of standard spans, non-standard span/specials spans supporting special track layouts. | Mayur
3.1 |  | Cable Profile - Layout | Mayur
3.2 |  | Shear Key Details | Mayur
3.3 |  | Reinforcement Details | Mayur
3.4 |  | Dimension Details | Mayur
4 |  | Preparation and submission of GAD | Mayur
5 |  | Bill of Quantities | Mayur
6 |  | Cost Estimate and specifications | Mayur
6.1 |  | Cost Estimate
6.2 |  | General Specifications
7 |  | Create Work Breakdown Structure (WBS) for its scope of work | Mayur
8 |  | 3D BIM Model | Mayur
9 |  | Preparation & Submission of Design Basis Report | Mayur
10 |  | preparation & Submission of the As built Drawings | Mayur
11.1 |  | Pile/open Foundation
11.2 |  | Pilecap & Pier
11.3 |  | Pier Cap
11.4 |  | Pier Arm
11.5 |  | Cable Profile - Layout
11.6 |  | Shear Key Details
11.7 |  | Dimension Details
11 |  | Design submission programme | Mayur
12 |  | Monthly- Progress Report | Mayur
13 |  | Design & Drawings of the Tempororary Work | Mayur
14 |  | Maintenance Report | Mayur
15 |  | inspection Checklist | Mayur
16 |  | Detail designs and GFCDs of Crashed Barrier, barricades, Inserts/shear connectors/starter bars for track plinth, parapets and MS railing, Man holes, Earthing arrangement, drainage system, inserts for signaling masts in the parapets and other | Mayur
16.1 |  | Crashed Barriers
16.2 |  | Barricades
16.3 |  | Inserts/Shear Connectors/Starter Bars for track Plinth
16.4 |  | MS Railing
16.5 |  | Manholes
16.6 |  | Earthing Arrangements
16.7 |  | Drainage System
16.8 |  | Inserts for Signalling masts
17 |  | Submission of soil investigation report | Mayur
18 |  | Detailed Design and Dawings of Launching System | Mayur
19 |  | Submission of pile load test report, plate test and other reports | Mayur
19.1 |  | Pile Load test report | Mayur
19.2 |  | Plate test | Mayur
20 |  | detailed traffic diversion plans | Mayur
21 |  | Quality Assurance plan | Mayur
22 |  | Survey Report | Mayur
23 |  | Utilities Report | Mayur
24 |  | Construction/Installation Analysis Report | Mayur
25 |  | Construction Method Statement | Mayur
26 |  | Submission of Master Plan for Property |  | Anurag
27 |  | Development Planning Criteria for Stations |  | Anurag
28 |  | Presentation of Design Alternatives and complete programme schedule |  | Anurag
29 |  | Schematic Design & Drawings |  | Anurag
30 |  | Data Base reports for design after compiling data and drawings of topographical surveys and geotechnical investigations |  | Anurag
31 |  | Traffic Management Plan and Other general Planning matters as required |  | Anurag
32 |  | General Arrangement Drawings including complete rail level profiles withing the scope of work |  | Anurag
33 |  | Tender Drawings and BOQ |  | Anurag
34 |  | Cost Estimates including detailed rate analysis of all items of work and specifications, tender volume of Employer's requirement |  | Anurag
35 |  | Issue of Good for construction drawings |  | Anurag
35.1 |  | Floor Plans |  | Anurag
35.2 |  | Elevation |  | Anurag
35.3 |  | Cross-section |  | Anurag
35.4 |  | Logitunal Section |  | Anurag
35.5 |  | Staircase details |  | Anurag
35.6 |  | Lift Details |  | Anurag
35.7 |  | Escalator Details |  | Anurag
35.8 |  | Roof Details |  | Anurag
35.9 |  | Flooring Details |  | Anurag
35.1 |  | Combined Service Drawing |  | Anurag
35.11 |  | Numeration & Reinforcement Drawing |  | Anurag
35.12 |  | Coordinate/Drawing Layouts |  | Anurag
35.13 |  | Framing Plans |  | Anurag
35.14 |  | Foundation |  | Anurag
35.15 |  | Substructure |  | Anurag
35.16 |  | SuperStructure Drawings |  | Anurag
36 |  | Submission of originals & Design Report |  | Anurag
37 |  | Construction Support Activities |  | Anurag
38 |  | Invoices or Bills |  | Anurag
39 |  | Weekly Progress Report |  | Anurag
40 |  | Monthly Progres Report |  | Anurag
41 |  | Checklist |  | Anurag
42 |  | Interface Drawings |  | Anurag
43 |  | Construction Programmes |  | Anurag
44 |  | Project Management Plan |  |  | Tech. Spec.
45 |  | Contractor's Project Plan |  |  | Tech. Spec.
46 |  | Interface Management Plan |  |  | Tech. Spec.
47 |  | Quality Plans |  |  | Tech. Spec.
48 |  | Safety Plans |  |  | Tech. Spec.
49 |  | Electromagnetic Compatibility Management Plan |  |  | Tech. Spec.
50 |  | Software Quality Assurance Plan |  |  | Tech. Spec.
51 |  | Design Plan |  |  | Tech. Spec.
52 |  | Design Verification and Validation Plan |  |  | Tech. Spec.
53 |  | Factory Testing Plan |  |  | Tech. Spec.
54 |  | Procurement, Manufacturing and Delivery Plan |  |  | Tech. Spec.
55 |  | Construction and Installation Plan |  |  | Tech. Spec.
56 |  | Health and Safety Documentaion |  |  | Tech. Spec.
57 |  | Environmental Qualities Managemen Plan |  |  | Tech. Spec.
58 |  | Environmental Mitigation Implementation Schedule |  |  | Tech. Spec.
59 |  | Traffic Management Submissions |  |  | Tech. Spec.
60 |  | Commissiong Plan |  |  | Tech. Spec.
61 |  | Operation and Maintenance Manual Plan |  |  | Tech. Spec.
62 |  | Training and Transfer of Technology Plan |  |  | Tech. Spec.
63 |  | Spares Management Plan |  |  | Tech. Spec.
64 |  | Defects Liability Management Plan |  |  | Tech. Spec.
65 |  | Fire Safety Plan |  |  |  |  | Kshitiz
66 |  | Site Management Plan |  |  |  |  | Kshitiz
67 |  | Installation Plan |  |  |  |  | Kshitiz
68 |  | Testing and Commissioning Management Plan |  |  |  |  | Kshitiz
69 |  | Defects Liability Management Plan |  |  |  |  | Kshitiz
70 |  | Maintenance Plan |  |  |  |  | Kshitiz
71 |  | Quality Management Plan, & Quality Plan |  |  |  |  | Kshitiz
72 |  | HSE Plan |  |  |  |  | Kshitiz
73 |  | Project Management Plan |  |  |  |  | Kshitiz
74 |  | Interface Management Plan |  |  |  |  | Kshitiz
75 |  | RAM Plan |  |  |  |  | Kshitiz
76 |  | Safety Plan |  |  |  |  | Kshitiz
77 |  | Knowledge Sharing Plan |  |  |  |  | Kshitiz
78 |  | EMC Plan |  |  |  |  | Kshitiz
79 |  | Design Management Plan |  |  |  |  | Kshitiz
80 |  | Software Quality Assurance Plan |  |  |  |  | Kshitiz
81 |  | Procurement Management Plan (part of Manufacturing and Delivery Plan) |  |  |  |  | Kshitiz
82 |  | Transportation of Equipment Plan (part of Manufacturing and Delivery Plan) |  |  |  |  | Kshitiz
83 |  | Works Plan |  |  |  |  | Kshitiz
84 |  | COM PHA Report |  |  |  |  | Kshitiz
85 |  | COM IHA Report |  |  |  |  | Kshitiz
86 |  | COM SSHA Report |  |  |  |  | Kshitiz
87 |  | COM OSHA report |  |  |  |  | Kshitiz
88 |  | COM Hazard Log |  |  |  |  | Kshitiz
89 |  | COM Safety Case (Design Phase) |  |  |  |  | Kshitiz
90 |  | COM Safety Case (Commissioning Phase) |  |  |  |  | Kshitiz
91 |  | COM RAM Analysis |  |  |  |  | Kshitiz
92 |  | COM RAMS Demonstration Plan |  |  |  |  | Kshitiz
93 |  | Design Verification Table and Matrix of compliance |  |  |  |  | Kshitiz
94 |  | Conceptual Design - FOTS |  |  |  |  | Kshitiz
95 |  | Conceptual Design - PAS |  |  |  |  | Kshitiz
96 |  | Conceptual Design - PIDS |  |  |  |  | Kshitiz
97 |  | Conceptual Design - Master Clock System |  |  |  |  | Kshitiz
98 |  | Conceptual Design - CDRS |  |  |  |  | Kshitiz
99 |  | Conceptual Design - Telephone System |  |  |  |  | Kshitiz
100 |  | Conceptual Design - T - SCADA |  |  |  |  | Kshitiz
101 |  | Conceptual Design - Radio System |  |  |  |  | Kshitiz
102 |  | Conceptual Design - CCTV |  |  |  |  | Kshitiz
103 |  | Conceptual Design - OA & IT |  |  |  |  | Kshitiz
104 |  | Conceptual Design - Access Control |  |  |  |  | Kshitiz
105 |  | Conceptual Design - Cables Power |  |  |  |  | Kshitiz
106 |  | Conceptual Design - Cables Data |  |  |  |  | Kshitiz
107 |  | Conceptual Design - Interface - Internal |  |  |  |  | Kshitiz
108 |  | Conceptual Design - Interface - External |  |  |  |  | Kshitiz
109 |  | Vendor Approval for Systems and Sub Systems |  |  |  |  | Kshitiz
110 |  | Telephone Numbering Plan |  |  |  |  | Kshitiz
111 |  | Equipment & Cable Labeling Plan |  |  |  |  | Kshitiz
112 |  | Preliminary Design - FOTS |  |  |  |  | Kshitiz
113 |  | Preliminary Design - PAS |  |  |  |  | Kshitiz
114 |  | Preliminary Design - PIDS |  |  |  |  | Kshitiz
115 |  | Preliminary Design - Master Clock System |  |  |  |  | Kshitiz
116 |  | Preliminary Design - Telephone System |  |  |  |  | Kshitiz
117 |  | Preliminary Design - Radio System |  |  |  |  | Kshitiz
118 |  | Preliminary Design - CCTV |  |  |  |  | Kshitiz
119 |  | Preliminary Design - OA & IT |  |  |  |  | Kshitiz
120 |  | Preliminary Design - Access Control |  |  |  |  | Kshitiz
121 |  | Preliminary Design - CDRS |  |  |  |  | Kshitiz
122 |  | Preliminary Design - T - SCADA |  |  |  |  | Kshitiz
123 |  | Detailed Design - FOTS |  |  |  |  | Kshitiz
124 |  | Detailed Design - PAS |  |  |  |  | Kshitiz
125 |  | Detailed Design - PIDS |  |  |  |  | Kshitiz
126 |  | Detailed Design - Master Clock System |  |  |  |  | Kshitiz
127 |  | Detailed Design - Telephone System |  |  |  |  | Kshitiz
128 |  | Detailed Design - Radio System |  |  |  |  | Kshitiz
129 |  | Detailed Design - CCTV |  |  |  |  | Kshitiz
130 |  | Detailed Design - OA & IT |  |  |  |  | Kshitiz
131 |  | Detailed Design - Access Control |  |  |  |  | Kshitiz
132 |  | Detailed Design - CDRS |  |  |  |  | Kshitiz
133 |  | Detailed Design - T - SCADA |  |  |  |  | Kshitiz
134 |  | Detailed Design - Cables Power |  |  |  |  | Kshitiz
135 |  | Detailed Design - Cables Data |  |  |  |  | Kshitiz
136 |  | Detailed Interface Document - COMs & S&TC |  |  |  |  | Kshitiz
137 |  | Detailed Interface Document - COMs & AFC |  |  |  |  | Kshitiz
138 |  | Detailed Interface Document - COMs & Rolling Stock |  |  |  |  | Kshitiz
139 |  | Detailed Interface Document - COMs & SCADA |  |  |  |  | Kshitiz
140 |  | Detailed Interface Document - COMs & UPS |  |  |  |  | Kshitiz
141 |  | Detailed Interface Document - COMs & Civil Works |  |  |  |  | Kshitiz
142 |  | Detailed Interface Document - COMs & Traction Power |  |  |  |  | Kshitiz
143 |  | Detailed Interface Document - COMs & MEP |  |  |  |  | Kshitiz
144 |  | Detailed Interface Document - COMs & Power Supply Contractor |  |  |  |  | Kshitiz
145 |  | Detailed Interface Document - COMs & Lift & Escalator |  |  |  |  | Kshitiz
146 |  | Detailed Interface Document - COMs & BMS |  |  |  |  | Kshitiz
147 |  | FAT Plan - FOTS |  |  |  |  | Kshitiz
148 |  | FAT Plan - PAS |  |  |  |  | Kshitiz
149 |  | FAT Plan - PIDS |  |  |  |  | Kshitiz
150 |  | FAT Plan- Master Clock System |  |  |  |  | Kshitiz
151 |  | FAT Plan - Telephone System |  |  |  |  | Kshitiz
152 |  | FAT Plan - Radio System |  |  |  |  | Kshitiz
153 |  | FAT Plan - CCTV |  |  |  |  | Kshitiz
154 |  | FAT Plan - OA & IT |  |  |  |  | Kshitiz
155 |  | FAT Plan - Access Control |  |  |  |  | Kshitiz
156 |  | FAT Plan - CDRS |  |  |  |  | Kshitiz
157 |  | FAT Plan - T - SCADA |  |  |  |  | Kshitiz
158 |  | FAT Plan - Power Cables |  |  |  |  | Kshitiz
159 |  | FAT Plan - Data Cables |  |  |  |  | Kshitiz
160 |  | FAT Plan - OFC Cables |  |  |  |  | Kshitiz
161 |  | FAT Plan - Racks Cables |  |  |  |  | Kshitiz
162 |  | FAT Plan - Mechanical Structures etc |  |  |  |  | Kshitiz
163 |  | Installation Drawing - Block Wiring Diagram - FOTS |  |  |  |  | Kshitiz
164 |  | Installation Drawing - Block Wiring Diagram - PAS |  |  |  |  | Kshitiz
165 |  | Installation Drawing - Block Wiring Diagram - PIDS |  |  |  |  | Kshitiz
166 |  | Installation Drawing - Block Wiring Diagram - Master Clock System |  |  |  |  | Kshitiz
167 |  | Installation Drawing - Block Wiring Diagram - Telephone System |  |  |  |  | Kshitiz
168 |  | Installation Drawing - Block Wiring Diagram - Radio System |  |  |  |  | Kshitiz
169 |  | Installation Drawing - Block Wiring Diagram - CCTV |  |  |  |  | Kshitiz
170 |  | Installation Drawing - Block Wiring Diagram - OA & IT |  |  |  |  | Kshitiz
171 |  | Installation Drawing - Block Wiring Diagram - Access Control |  |  |  |  | Kshitiz
172 |  | Installation Drawing - Block Wiring Diagram - CDRS |  |  |  |  | Kshitiz
173 |  | Installation Drawing - Block Wiring Diagram - T - SCADA |  |  |  |  | Kshitiz
174 |  | Installation Drawing - Equipment & Cable Layout Plan - FOTS |  |  |  |  | Kshitiz
175 |  | Installation Drawing - Equipment & Cable Layout Plan - PAS |  |  |  |  | Kshitiz
176 |  | Installation Drawing - Equipment & Cable Layout Plan - PIDS |  |  |  |  | Kshitiz
177 |  | Installation Drawing - Equipment & Cable Layout Plan - Master Clock System |  |  |  |  | Kshitiz
178 |  | Installation Drawing - Equipment & Cable Layout Plan - Telephone System |  |  |  |  | Kshitiz
179 |  | Installation Drawing - Equipment & Cable Layout Plan - Radio System |  |  |  |  | Kshitiz
180 |  | Installation Drawing - Equipment & Cable Layout Plan - CCTV |  |  |  |  | Kshitiz
181 |  | Installation Drawing - Equipment & Cable Layout Plan - OA & IT |  |  |  |  | Kshitiz
182 |  | Installation Drawing - Equipment & Cable Layout Plan - Access Control |  |  |  |  | Kshitiz
183 |  | Installation Drawing - Equipment & Cable Layout Plan - CDRS |  |  |  |  | Kshitiz
184 |  | Installation Drawing - Equipment & Cable Layout Plan - T - SCADA |  |  |  |  | Kshitiz
185 |  | System Commissioning & Configuration Plan - FOTS |  |  |  |  | Kshitiz
186 |  | System Commissioning & Configuration Plan - PAS |  |  |  |  | Kshitiz
187 |  | System Commissioning & Configuration Plan - PIDS |  |  |  |  | Kshitiz
188 |  | System Commissioning & Configuration Plan - Master Clock |  |  |  |  | Kshitiz
189 |  | System Commissioning & Configuration Plan - Telephone System |  |  |  |  | Kshitiz
190 |  | System Commissioning & Configuration Plan - Radio System |  |  |  |  | Kshitiz
191 |  | System Commissioning & Configuration Plan - CCTV |  |  |  |  | Kshitiz
192 |  | System Commissioning & Configuration Plan - OA&IT |  |  |  |  | Kshitiz
193 |  | System Commissioning & Configuration Plan - Access Control |  |  |  |  | Kshitiz
194 |  | System Commissioning & Configuration Plan - CDRS |  |  |  |  | Kshitiz
195 |  | System Commissioning & Configuration Plan - T- SCADA |  |  |  |  | Kshitiz
196 |  | Operation Manual - FOTS |  |  |  |  | Kshitiz
197 |  | Operation Manual - PAS |  |  |  |  | Kshitiz
198 |  | Operation Manual - PIDS |  |  |  |  | Kshitiz
199 |  | Operation Manual - Master Clock |  |  |  |  | Kshitiz
200 |  | Operation Manual - Telephone System |  |  |  |  | Kshitiz
201 |  | Operation Manual - Radio System |  |  |  |  | Kshitiz
202 |  | Operation Manual - CCTV |  |  |  |  | Kshitiz
203 |  | Operation Manual - OA&IT |  |  |  |  | Kshitiz
204 |  | Operation Manual - Access Control |  |  |  |  | Kshitiz
205 |  | Operation Manual - CDRS |  |  |  |  | Kshitiz
206 |  | Operation Manual - T- SCADA |  |  |  |  | Kshitiz
207 |  | Maintenance Manual - FOTS |  |  |  |  | Kshitiz
208 |  | Maintenance Manual - PAS |  |  |  |  | Kshitiz
209 |  | Maintenance Manual - PIDS |  |  |  |  | Kshitiz
210 |  | Maintenance Manual - Master Clock |  |  |  |  | Kshitiz
211 |  | Maintenance Manual - Telephone System |  |  |  |  | Kshitiz
212 |  | Maintenance Manual - Radio System |  |  |  |  | Kshitiz
213 |  | Maintenance Manual - CCTV |  |  |  |  | Kshitiz
214 |  | Maintenance Manual - OA&IT |  |  |  |  | Kshitiz
215 |  | Maintenance Manual - Access Control |  |  |  |  | Kshitiz
216 |  | Maintenance Manual - CDRS |  |  |  |  | Kshitiz
217 |  | Maintenance Manual - T- SCADA |  |  |  |  | Kshitiz
218 |  | Preventive Maintenance Schedule |  |  |  |  | Kshitiz
219 |  | Training Manual - FOTS |  |  |  |  | Kshitiz
220 |  | Training Manual - PAS |  |  |  |  | Kshitiz
221 |  | Training Manual - PIDS |  |  |  |  | Kshitiz
222 |  | Training Manual - Master Clock |  |  |  |  | Kshitiz
223 |  | Training Manual - Telephone System |  |  |  |  | Kshitiz
224 |  | Training Manual - Radio System |  |  |  |  | Kshitiz
225 |  | Training Manual - CCTV |  |  |  |  | Kshitiz
226 |  | Training Manual - OA&IT |  |  |  |  | Kshitiz
227 |  | Training Manual - Access Control |  |  |  |  | Kshitiz
228 |  | Training Manual - CDRS |  |  |  |  | Kshitiz
229 |  | Training Manual - T- SCADA |  |  |  |  | Kshitiz
230 |  | Method of Statement - OFC Cable Laying & Termination |  |  |  |  | Kshitiz
231 |  | Method Statement - Power Cable Laying & Termination |  |  |  |  | Kshitiz
232 |  | Method Statement - Secondary Containment |  |  |  |  | Kshitiz
233 |  | Method Statement - Primary & Secondary Fixtures installation |  |  |  |  | Kshitiz
234 |  | Method Statement - End Equipment Installation at OCC & Depot |  |  |  |  | Kshitiz
235 |  | Method Statement - End Equipment Installation at Station |  |  |  |  | Kshitiz
236 |  | Method Statement - Equipment Installation in Telecom Racks |  |  |  |  | Kshitiz
237 |  | Method Statement - Equipment Installation On Board Equipment - Radio |  |  |  |  | Kshitiz
238 |  | Method Statement - CAT 6 and Structural Cabling |  |  |  |  | Kshitiz
239 |  | Method Statement -Radio Tower Foundation and Mast Installation |  |  |  |  | Kshitiz
240 |  | Method Statement -Out door Equipment Installation |  |  |  |  | Kshitiz
241 |  | Method Statement -Out door Cable Laying & Installation |  |  |  |  | Kshitiz
242 |  | Installation Test Plan - FOTS |  |  |  |  | Kshitiz
243 |  | Installation Test Plan - PAS |  |  |  |  | Kshitiz
244 |  | Installation Test Plan- PIDS |  |  |  |  | Kshitiz
245 |  | Installation Test Plan - Master Clock |  |  |  |  | Kshitiz
246 |  | Installation Test Plan- Telephone System |  |  |  |  | Kshitiz
247 |  | Installation Test Plan - Radio System |  |  |  |  | Kshitiz
248 |  | Installation Test Plan - CCTV |  |  |  |  | Kshitiz
249 |  | Installation Test Plan - OA&IT |  |  |  |  | Kshitiz
250 |  | Installation Test Plan - Access Control |  |  |  |  | Kshitiz
251 |  | Installation Test Plan - CDRS |  |  |  |  | Kshitiz
252 |  | Installation Test Plan - T- SCADA |  |  |  |  | Kshitiz
253 |  | Partial Acceptance Test Plan - FOTS |  |  |  |  | Kshitiz
254 |  | Partial Acceptance Test Plan - PAS |  |  |  |  | Kshitiz
255 |  | Partial Acceptance Test Plan- PIDS |  |  |  |  | Kshitiz
256 |  | Partial Acceptance Test Plan - Master Clock |  |  |  |  | Kshitiz
257 |  | Partial Acceptance Test Plan- Telephone System |  |  |  |  | Kshitiz
258 |  | Partial Acceptance Test Plan - Radio System |  |  |  |  | Kshitiz
259 |  | Partial Acceptance Test Plan - CCTV |  |  |  |  | Kshitiz
260 |  | Partial Acceptance Test Plan - OA&IT |  |  |  |  | Kshitiz
261 |  | Partial Acceptance Test Plan - Access Control |  |  |  |  | Kshitiz
262 |  | Partial Acceptance Test Plan - CDRS |  |  |  |  | Kshitiz
263 |  | Partial Acceptance Test Plan - T- SCADA |  |  |  |  | Kshitiz
264 |  | Partial Acceptance Test Plan - FOTS |  |  |  |  | Kshitiz
265 |  | System Acceptance Test Plan - PAS |  |  |  |  | Kshitiz
266 |  | System Acceptance Test Plan- PIDS |  |  |  |  | Kshitiz
267 |  | System Acceptance Test Plan - Master Clock |  |  |  |  | Kshitiz
268 |  | System Acceptance Test Plan- Telephone System |  |  |  |  | Kshitiz
269 |  | System Acceptance Test Plan - Radio System |  |  |  |  | Kshitiz
270 |  | System Acceptance Test Plan - CCTV |  |  |  |  | Kshitiz
271 |  | System Acceptance Test Plan - OA&IT |  |  |  |  | Kshitiz
272 |  | System Acceptance Test Plan - Access Control |  |  |  |  | Kshitiz
273 |  | System Acceptance Test Plan - CDRS |  |  |  |  | Kshitiz
274 |  | System Acceptance Test Plan - T- SCADA |  |  |  |  | Kshitiz
275 |  | Integrated Tests Plan - COMs & S&TC |  |  |  |  | Kshitiz
276 |  | Integrated Tests Plan - COMs & AFC |  |  |  |  | Kshitiz
277 |  | Integrated Tests Plan- COMs & Rolling Stock |  |  |  |  | Kshitiz
278 |  | Integrated Tests Plan- COMs & SCADA |  |  |  |  | Kshitiz
279 |  | Integrated Tests Plan - COMs & UPS |  |  |  |  | Kshitiz
280 |  | Integrated Tests Plan- COMs & Civil Works |  |  |  |  | Kshitiz
281 |  | Integrated Tests Plan - COMs & Traction Power |  |  |  |  | Kshitiz
282 |  | Integrated Tests Plan- COMs & MEP |  |  |  |  | Kshitiz
283 |  | Integrated Tests Plan COMs & Power Supply Contractor |  |  |  |  | Kshitiz
284 |  | Integrated Tests Plan - COMs & Lift & Escalator |  |  |  |  | Kshitiz
285 |  | Integrated Tests Plan- COMs & BMS |  |  |  |  | Kshitiz
286 |  | Handover Report & Document fro Approval |  |  |  |  | Kshitiz
287 |  | Tests Reports |  |  |  |  | Kshitiz
288 |  | Monthly Progress Reports |  |  |  |  | Kshitiz
289 |  | Interface Management Plan |  |  |  | Tech. Spec.
290 |  | Work Plan (Work Programme and Design Submission Programme) |  |  |  | Tech. Spec.
291 |  | Quality Assurance Plan |  |  |  | Tech. Spec.
292 |  | Quality Plan |  |  |  | Tech. Spec.
293 |  | System Safety Assurance Plan |  |  |  | Tech. Spec.
294 |  | Reliability, Availability and Maintainability Assurance Plan |  |  |  | Tech. Spec.
295 |  | Site Safety Plan |  |  |  | Tech. Spec.
296 |  | Software Quality Assurance Plan |  |  |  | Tech. Spec.
297 |  | Environmental Plan |  |  |  | Tech. Spec.
298 |  | Inspection, Test and Commissioning Plan |  |  |  | Tech. Spec.
299 |  | Manufacturing Schedule and Process Sequence Plan |  |  |  | Tech. Spec.
300 |  | Integration Tests and Instruentation Test protocol for Prototype Rake |  |  |  | Tech. Spec.
301 |  | Service Trails Protocol |  |  |  | Tech. Spec.
302 |  | Operational Safety Report |  |  |  | Tech. Spec.
303 |  | Monthly Progress Reports |  |  |  | Tech. Spec.
304 |  | Procurement Report |  |  |  | Tech. Spec.
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418

## Master Deliverable List
Master Deliverable List
Doc Code | Type | Group Code | MDL Code | Group/ Class | Document
|  | PPM |  | Project & Programme Management
TDP | Non-CAD |  | PPM.TDP | Project & Programme Management | Traffic Diversion Plans
TMP | Non-CAD |  | PPM.TMP | Project & Programme Management | Traffic Management Plan
BOQ | Non-CAD |  | PPM.BOQ | Project & Programme Management | Bill of Quantities
CET | Non-CAD |  | PPM.CET | Project & Programme Management | Cost Estimate
GSP | Non-CAD |  | PPM.GSP | Project & Programme Management | General Specifications
WBS | Non-CAD |  | PPM.WBS | Project & Programme Management | Work Breakdown Structure (WBS)
SUB | Non-CAD |  | PPM.SUB | Project & Programme Management | Master Information Delivery Plan (MIDP)
MPP | Non-CAD |  | PPM.MPP | Project & Programme Management | Master Plan for Property
PRE | Non-CAD |  | PPM.PRE | Project & Programme Management | Pre-Contract BIM Execution Plan
POS | Non-CAD |  | PPM.POS | Project & Programme Management | Post-Contract BIM Execution Plan
EIR | Non-CAD |  | PPM.EIR | Project & Programme Management | Employer`s Information Requirements
SMP | Non-CAD |  | PPM.SMP | Project & Programme Management | Standard Methods and Procedures
CAD | Non-CAD |  | PPM.CAD | Project & Programme Management | Cad Standard
TML | Non-CAD |  | PPM.TML | Project & Programme Management | Training Manual
DID | Non-CAD |  | PPM.DID | Project & Programme Management | Detailed Interface Document
PRT | Non-CAD |  | PPM.PRT | Project & Programme Management | Procurement Report
MGP | Non-CAD |  | PPM.MGP | Project & Programme Management | Management Quality Plan
MQP | Non-CAD |  | PPM.MQP | Project & Programme Management | Manufacturing Quality Plan
AFI | Non-CAD |  | PPM.AFI | Project & Programme Management | Automatic fault identification and isolation arrangement
SPR | Non-CAD |  | PPM.SPR | Project & Programme Management | Space Requirements
HIC | Non-CAD |  | PPM.HIC | Project & Programme Management | Hazard Identification and Control Plan
SOI | Non-CAD |  | PPM.SOI | Project & Programme Management | Schedule of Inspection and Test Plans
TPL | Non-CAD |  | PPM.TPL | Project & Programme Management | Training Plan
SUP | Non-CAD |  | PPM.SUP | Project & Programme Management | Sustainable Transport Plan
SPS | Non-CAD |  | PPM.SPS | Project & Programme Management | Surface Preparation / Painting Specification
MPD | Non-CAD |  | PPM.MPD | Project & Programme Management | Master Information Production and Delivery Table (MPDT)
CON | Non-CAD |  | PPM.CON | Project & Programme Management | Contract Document
ORG | Non-CAD |  | PPM.ORG | Project & Programme Management | Organization Chart
COM | Non-CAD |  | PPM.COM | Project & Programme Management | Competency Management Plan
CMT | Non-CAD |  | PPM.CMT | Project & Programme Management | Competency Matrix
LRD | Non-CAD |  | PPM.LRD | Project & Programme Management | Labour Records
SIP | Non-CAD |  | PPM.SIP | Project & Programme Management | Site Management Plan
ECR | Non-CAD |  | PPM.ECR | Project & Programme Management | Earthworks Compaction Records
IRC | Non-CAD |  | PPM.IRC | Project & Programme Management | Inspection release certificates
MAP | Non-CAD |  | PPM.MAP | Project & Programme Management | Material Proposal Schedule
MAC | Non-CAD |  | PPM.MAC | Project & Programme Management | Material Compliance Record
MPC | Non-CAD |  | PPM.MPC | Project & Programme Management | Material & Product Certificates
SCO | Non-CAD |  | PPM.SCO | Project & Programme Management | Sub construction & Construction Certificates
WCC | Non-CAD |  | PPM.WCC | Project & Programme Management | Whole Contract Construction Certificate
KPI | Non-CAD |  | PPM.KPI | Project & Programme Management | Key Performance Index Reports
LKP | Non-CAD |  | PPM.LKP | Project & Programme Management | List of Key Performance Index
CMP | Non-CAD |  | PPM.CMP | Project & Programme Management | Consents Management Plan
SSS | Non-CAD |  | PPM.SSS | Project & Programme Management | Schedule of Subcontractors and suppliers
CTO | Non-CAD |  | PPM.CTO | Project & Programme Management | Contract Take over certificate
CCC | Non-CAD |  | PPM.CCC | Project & Programme Management | Contract Completion Certificate
RLS | Non-CAD |  | PPM.RLS | Project & Programme Management | Recommended List of Spares
TST | Non-CAD |  | PPM.TST | Project & Programme Management | Training Strategy
IRF | Non-CAD |  | PPM.IRF | Project & Programme Management | Installation Release Note
PCS | Non-CAD |  | PPM.PCS | Project & Programme Management | Planning Criteria for Stations
CIA | Non-CAD |  | PPM.CIA | Project & Programme Management | Critical Items Action Report
MOM | Non-CAD |  | PPM.MOM | Project & Programme Management | Minutes of Meetings
SDP | Non-CAD |  | PPM.SDP | Project & Programme Management | Supplier Diversity Plan
PSS | Non-CAD |  | PPM.PSS | Project & Programme Management | Planned Surveillance Schedule
SWM | Non-CAD |  | PPM.SWM | Project & Programme Management | Site Waste Management Plan
IRN | Non-CAD |  | PPM.IRN | Project & Programme Management | Inspection Release Notes
AUS | Non-CAD |  | PPM.AUS | Project & Programme Management | Audit Schedules
ETS | Non-CAD |  | PPM.ETS | Project & Programme Management | Environmental and traffic surveys (Detailed scopes, method statements, risk assessments and other requirements statements)
SRS | Non-CAD |  | PPM.SRS | Project & Programme Management | System Requirement Specification
MCP | Non-CAD |  | PPM.MCP | Project & Programme Management | Electromagnetic Compatibility Management Control Plan
CHE | Non-CAD |  | PPM.CHE | Project & Programme Management | Checklist
ECM | Non-CAD |  | PPM.ECM | Project & Programme Management | Electromagnetic Compatibility Management Plan
PMD | Non-CAD |  | PPM.PMD | Project & Programme Management | Procurement, Manufacturing and Delivery Plan
PMP | Non-CAD |  | PPM.PMP | Project & Programme Management | Project Management Plan
IMP | Non-CAD |  | PPM.IMP | Project & Programme Management | Interface Management Plan
VAL | Non-CAD |  | PPM.VAL | Project & Programme Management | Vendor Approval
TNP | Non-CAD |  | PPM.TNP | Project & Programme Management | Telephone Numbering Plan
CMM | Non-CAD |  | PPM.CMM | Project & Programme Management | Commissionng Management Plan
DDD | Non-CAD |  | PPM.DDD | Project & Programme Management | Detailed Description
FDP | Non-CAD |  | PPM.FDP | Project & Programme Management | Functional Description
GID | Non-CAD |  | PPM.GID | Project & Programme Management | General Installation Document
IML | Non-CAD |  | PPM.IML | Project & Programme Management | Installation Manual
GDT | Non-CAD |  | PPM.GDT | Project & Programme Management | General Description
TSP | Non-CAD |  | PPM.TSP | Project & Programme Management | Technicon Specification
KSP | Non-CAD |  | PPM.KSP | Project & Programme Management | Knowledge Sharing Plan
PRM | Non-CAD |  | PPM.PRM | Project & Programme Management | Procurement Management Plan
MPS | Non-CAD |  | PPM.MPS | Project & Programme Management | Manufacturing Schedule and Process Sequence Plan
STP | Non-CAD |  | PPM.STP | Project & Programme Management | Service Trails Protocol
MPR | Non-CAD |  | PPM.MPR | Project & Programme Management | Monthly-Progress Report
PCP | Non-CAD |  | PPM.PCP | Project & Programme Management | Project Controls Plan
CVR | Non-CAD |  | PPM.CVR | Project & Programme Management | Cost/Value Reports
DAR | Non-CAD |  | PPM.DAR | Project & Programme Management | Daily Reports
QRP | Non-CAD |  | PPM.QRP | Project & Programme Management | Quarterly Report Period Progress Report
RFI | Non-CAD |  | PPM.RFI | Project & Programme Management | Request for Inspection
URT | Non-CAD |  | PPM.URT | Project & Programme Management | Utilities Report
WPR | Non-CAD |  | PPM.WPR | Project & Programme Management | Weekly Progress Report
SSR | Non-CAD |  | PPM.SSR | Project & Programme Management | Surveillance Sheet Reports
INR | Non-CAD |  | PPM.INR | Project & Programme Management | Interface Reports
|  | BER |  | Building & Equipment Records
SIR | Non-CAD |  | BER.SIR | Building & Equipment Records | Soil Investigation Report
SLR | Non-CAD |  | BER.SLR | Building & Equipment Records | Span Load Test Reports
STR | Non-CAD |  | BER.STR | Building & Equipment Records | Site acceptance test reports
SSD | Non-CAD |  | BER.SSD | Building & Equipment Records | Structural settlement/damage reports/summaries
SLE | Non-CAD |  | BER.SLE | Building & Equipment Records | Span Load Test Records
SLP | Non-CAD |  | BER.SLP | Building & Equipment Records | Span Load Test Plans
SIT | Non-CAD |  | BER.SIT | Building & Equipment Records | Site Test Report
SIS | Non-CAD |  | BER.SIS | Building & Equipment Records | Signage Schedules
PIT | Non-CAD |  | BER.PIT | Building & Equipment Records | Pile Load Test Report
SRT | Non-CAD |  | BER.SRT | Building & Equipment Records | Survey Report
PLT | Non-CAD |  | BER.PLT | Building & Equipment Records | Plate Load Test Report
AHB | Non-CAD |  | BER.AHB | Building & Equipment Records | Archaeological and historical building records
RMD | Non-CAD |  | BER.RMD | Building & Equipment Records | Records of modifications made to the completed infrastructure or installed equipment
PIN | Non-CAD |  | BER.PIN | Building & Equipment Records | Pile Integrity Test
UPV | Non-CAD |  | BER.UPV | Building & Equipment Records | UPV Test Report
POT | Non-CAD |  | BER.POT | Building & Equipment Records | Pull Out Test
INP | Non-CAD |  | BER.INP | Building & Equipment Records | Installation Plan
TEP | Non-CAD |  | BER.TEP | Building & Equipment Records | Tranportation of Equipment Plan
ECL | Non-CAD |  | BER.ECL | Building & Equipment Records | Equipment & Cable Labeling Plan
HRD | Non-CAD |  | BER.HRD | Building & Equipment Records | Handover Report & Document for Approval
ERT | Non-CAD |  | BER.ERT | Building & Equipment Records | Equipment Ratings
DAB | Non-CAD |  | BER.DAB | Building & Equipment Records | Drawing- As-built
ERD | Non-CAD |  | BER.ERD | Building & Equipment Records | Equipment Records
ABD | Non-CAD |  | BER.ABD | Building & Equipment Records | As Built Design Compliance Certificate
IRT | Non-CAD |  | BER.IRT | Building & Equipment Records | Inspection Report
EQS | Non-CAD |  | BER.EQS | Building & Equipment Records | Equipment Schedules
|  | CTP |  | Construction Process
CAR | Non-CAD |  | CTP.CAR | Construction Process | Construction/Installation Analysis Report
DTW | CAD |  | CTP.DTW | Building & Equipment Records | Drawing- Temporary Work
CMD | Non-CAD |  | CTP.CMD | Construction Process | Construction Methodology
MST | Non-CAD |  | CTP.MST | Construction Process | Method Statement
EMP | Non-CAD |  | CTP.EMP | Construction Process | Excavated Materials Plan
SBS | Non-CAD |  | CTP.SBS | Construction Process | Stations Building Services
MOF | Non-CAD |  | CTP.MOF | Construction Process | Modularisation & Off Site Assembly Plan
SMS | Non-CAD |  | CTP.SMS | Construction Process | Schedule of Method Statements
PRD | Non-CAD |  | CTP.PRD | Construction Process | Piling Records
PPC | Non-CAD |  | CTP.PPC | Construction Process | Pre and Post Concrete Pour Records
GTR | Non-CAD |  | CTP.GTR | Construction Process | Ground Treatment Records
UPL | Non-CAD |  | CTP.UPL | Construction Process | Utilities Plan
SSW | Non-CAD |  | CTP.SSW | Construction Process | Site Start Work Check list
PCC | Non-CAD |  | CTP.PCC | Construction Process | Pre-Start Construction Check List
LCC | Non-CAD |  | CTP.LCC | Construction Process | List of critical construction starts
CPH | Non-CAD |  | CTP.CPH | Construction Process | Construction Phase Plan
ROC | Non-CAD |  | CTP.ROC | Construction Process | Records Of Construction
CSA | Non-CAD |  | CTP.CSA | Construction Process | Construction Support Activities
|  | HSE |  | Health, Safety, Security and Environment
EQM | Non-CAD |  | HSE.EQM | Health, Safety, Security and Environment | Environmental Qualities Managemen Plan
CDP | Non-CAD |  | HSE.CDP | Health, Safety, Security and Environment | COM Safety Case (Design Phase)
CSP | Non-CAD |  | HSE.CSP | Health, Safety, Security and Environment | Contract Security Plan
SAP | Non-CAD |  | HSE.SAP | Health, Safety, Security and Environment | Safety Plan
SSA | Non-CAD |  | HSE.SSA | Health, Safety, Security and Environment | System Safety Assurance Plan
FSP | Non-CAD |  | HSE.FSP | Health, Safety, Security and Environment | Fire Safety Plan
EMI | Non-CAD |  | HSE.EMI | Health, Safety, Security and Environment | Environmental Mitigation Implementation Schedule
HSP | Non-CAD |  | HSE.HSP | Health, Safety, Security and Environment | HSE Plan
SSP | Non-CAD |  | HSE.SSP | Health, Safety, Security and Environment | Site Safety Plan
ENP | Non-CAD |  | HSE.ENP | Health, Safety, Security and Environment | Environmental Plan
OSR | Non-CAD |  | HSE.OSR | Health, Safety, Security and Environment | Operational Safety Report
SRE | Non-CAD |  | HSE.SRE | Health, Safety, Security and Environment | Safety Report
SEF | Non-CAD |  | HSE.SEF | Health, Safety, Security and Environment | HSE Files
SAR | Non-CAD |  | HSE.SAR | Health, Safety, Security and Environment | Safety Risk Assessment
SAJ | Non-CAD |  | HSE.SAJ | Health, Safety, Security and Environment | Safety Justifications
SRA | Non-CAD |  | HSE.SRA | Health, Safety, Security and Environment | Safety Risk Assessment Log
CRR | Non-CAD |  | HSE.CRR | Health, Safety, Security and Environment | Comparative Safety Related Risk Assessments
SER | Non-CAD |  | HSE.SER | Health, Safety, Security and Environment | HSE Reports
|  | OMR |  | Operation and Maintenance Records
OML | Non-CAD |  | OMR.OML | Operation and Maintenance Records | Operation Manual
PSP | Non-CAD |  | OMR.PSP | Operation and Maintenance Records | Performance Specification
SPM | Non-CAD |  | OMR.SPM | Operation and Maintenance Records | Spares Management Plan
DLM | Non-CAD |  | OMR.DLM | Operation and Maintenance Records | Defects Liability Management Plan
MML | Non-CAD |  | OMR.MML | Operation and Maintenance Records | Maintenance Manual
MRT | Non-CAD |  | OMR.MRT | Operation and Maintenance Records | Maintenance Report
OMM | Non-CAD |  | OMR.OMM | Operation and Maintenance Records | Operation and Maintenance Manual Plan
TTT | Non-CAD |  | OMR.TTT | Operation and Maintenance Records | Training and Transfer of Technology Plan
OPM | Non-CAD |  | OMR.OPM | Operation and Maintenance Records | Operational Manuals
PMS | Non-CAD |  | OMR.PMS | Operation and Maintenance Records | Preventive Maintenance Schedule
MRD | Non-CAD |  | OMR.MRD | Operation and Maintenance Records | Maintenance Records – Plant & Equipment
|  | TCR |  | Test and Commissioning Records
TCC | Non-CAD |  | TCR.TCC | Test and Commissioning Records | Test and Commissioning Certificates
CSC | Non-CAD |  | TCR.CSC | Test and Commissioning Records | COM Safety Case (Commissioning Phase)
CHL | Non-CAD |  | TCR.CHL | Test and Commissioning Records | Com Hazard Log
RMP | Non-CAD |  | TCR.RMP | Test and Commissioning Records | Ram Plan
RAM | Non-CAD |  | TCR.RAM | Test and Commissioning Records | RAM Report
RMG | Non-CAD |  | TCR.RMG | Test and Commissioning Records | RAM Management Plan
RAS | Non-CAD |  | TCR.RAS | Test and Commissioning Records | RAM Assessments
EMC | Non-CAD |  | TCR.EMC | Test and Commissioning Records | EMC Plan
CRA | Non-CAD |  | TCR.CRA | Test and Commissioning Records | Com Ram Analysis
CRD | Non-CAD |  | TCR.CRD | Test and Commissioning Records | Com Rams Demonstration Plan
RAP | Non-CAD |  | TCR.RAP | Test and Commissioning Records | RAM Assurance Plan
COR | Non-CAD |  | TCR.COR | Test and Commissioning Records | Com Pha Report
CIR | Non-CAD |  | TCR.CIR | Test and Commissioning Records | Com Iha Report
CSR | Non-CAD |  | TCR.CSR | Test and Commissioning Records | Com Ssha Report
COS | Non-CAD |  | TCR.COS | Test and Commissioning Records | Com Osha Report
ICL | Non-CAD |  | TCR.ICL | Test and Commissioning Records | Inspection Checklist
TCM | Non-CAD |  | TCR.TCM | Test and Commissioning Records | Testing Plan
FTP | Non-CAD |  | TCR.FTP | Test and Commissioning Records | Factory Testing Plan
FAP | Non-CAD |  | TCR.FAP | Test and Commissioning Records | Fat Plan
SCC | Non-CAD |  | TCR.SCC | Test and Commissioning Records | System Commissioning & Configuration Plan
ITP | Non-CAD |  | TCR.ITP | Test and Commissioning Records | Installation Test Plan
PAT | Non-CAD |  | TCR.PAT | Test and Commissioning Records | Partial Acceptance Test Plan
SAT | Non-CAD |  | TCR.SAT | Test and Commissioning Records | System Acceptance Test Plan
INT | Non-CAD |  | TCR.INT | Test and Commissioning Records | Integrated Tests Plan
TRP | Non-CAD |  | TCR.TRP | Test and Commissioning Records | Test Reports
ITC | Non-CAD |  | TCR.ITC | Test and Commissioning Records | Inspection, Test and Commissioning Plan
ITI | Non-CAD |  | TCR.ITI | Test and Commissioning Records | Integration Tests and Instrumentation Test protocol for Prototype Rake
INS | Non-CAD |  | TCR.INS | Test and Commissioning Records | Inspection and Test Plans
ITR | Non-CAD |  | TCR.ITR | Test and Commissioning Records | Inspection and Test Records
IRE | Non-CAD |  | TCR.IRE | Test and Commissioning Records | Inspection and Test Reports
TTR | Non-CAD |  | TCR.TTR | Test and Commissioning Records | Type Test Reports - Equipment
|  | DEG |  | Design
GDP | Non-CAD |  | DEG.GDP | Design | General Design Philosophy
DPP | Non-CAD |  | DEG.DPP | Design | Design and proving protection devices/systems and its validation
DES | Non-CAD |  | DEG.DES | Design | Design Reports
DVM | Non-CAD |  | DEG.DVM | Design | Design Verification and Matrix of Compliance
COD | Non-CAD |  | DEG.COD | Design | Conceptual Design
3DM | CAD |  | DEG.3DM | Design | 3D Model
DBR | Non-CAD |  | DEG.DBR | Design | Design Basis Report
DQP | Non-CAD |  | DEG.DQP | Design | Design Quality Plan
DNT | Non-CAD |  | DEG.DNT | Design | Design Note
DAT | Non-CAD |  | DEG.DAT | Design | Design Alternatives
DVV | Non-CAD |  | DEG.DVV | Design | Design Verification and Validation Plan
MDR | CAD |  | DEG.MDR | Design | Model Rendition (Coordination Model i.e. i--imodel or 3D PDF)
DIN | CAD |  | DEG.DIN | Design | Drawing- Interface
DMS | CAD |  | DEG.DMS | Design | Drawings- Miscellaneous sketches
DLG | CAD |  | DEG.DLG | Design | Drawings-Launching Grids
DFW | CAD |  | DEG.DFW | Design | Drawings-False work
DDP | CAD |  | DEG.DDP | Design | Drawings- Dimension Profile
DGA | CAD |  | DEG.DGA | Design | Drawings-General Arangement Drawing
DRP | CAD |  | DEG.DRP | Design | Drawing – Plan
DRC | CAD |  | DEG.DRC | Design | Drawing – Combined GA, Elevation, Section
DRS | CAD |  | DEG.DRS | Design | Drawing – Schematic
DSE | CAD |  | DEG.DSE | Design | Drawing – Section
DSC | CAD |  | DEG.DSC | Design | Drawing – Schedule
DLD | CAD |  | DEG.DLD | Design | Drawing – Line Diagram
DSO | CAD |  | DEG.DSO | Design | Drawing - Setting Out
DST | CAD |  | DEG.DST | Design | Drawing - Site Plan
DSU | CAD |  | DEG.DSU | Design | Drawing – Survey
DDT | CAD |  | DEG.DDT | Design | Drawing – Detail
DDE | CAD |  | DEG.DDE | Design | Drawing – Elevation
DDN | CAD |  | DEG.DDN | Design | Drawing- Numeration
DRE | CAD |  | DEG.DRE | Design | Drawing-Reinforcement
DCL | CAD |  | DEG.DCL | Design | Drawing - Design Calculation
SLD | CAD |  | DEG.SLD | Design | Drawing - SLD (Single Line Diagram)
DFP | CAD |  | DEG.DFP | Design | Drawing- Framing Plans
DPE | Non-CAD |  | DEG.DPE | Design | Design Package Execution Plan
DVE | Non-CAD |  | DEG.DVE | Design | Design Verification Plan
DVA | Non-CAD |  | DEG.DVA | Design | Design Validation Plan
DCP | Non-CAD |  | DEG.DCP | Design | Design and Checking Procedures
CDM | Non-CAD |  | DEG.CDM | Design | Designer’s CDM Risk Register
DEC | Non-CAD |  | DEG.DEC | Design | Design Certificates
DCC | Non-CAD |  | DEG.DCC | Design | Design Check Certificates
DCO | Non-CAD |  | DEG.DCO | Design | Design Completion Certificate (DCC)
CSD | Non-CAD |  | DEG.CSD | Design | Drawing- Combined Service Drawing
IDB | CAD |  | DEG.IDB | Design | Installation Drawing - Block Wiring Diagram
PSD | CAD |  | DEG.PSD | Design | Drawing - PreStressed Drawing
DGG | CAD |  | DEG.DGG | Design | Drawing- General Notes
IDE | CAD |  | DEG.IDE | Design | Installation Drawing - Equipment & Cable Layout Plan
BBS | CAD |  | DEG.BBS | Design | Bar Bending Schedule
SHD | CAD |  | DEG.SHD | Design | Shop Drawings
|  | QLY |  | Quality
QAR | Non-CAD |  | QLY.QAR | Quality | Quality Audit Reports
SQA | Non-CAD |  | QLY.SQA | Quality | Software Quality Assurance Plan
SQP | Non-CAD |  | QLY.SQP | Quality | Site Quality Plan
NCR | Non-CAD |  | QLY.NCR | Quality | Non-Conformance Reports
QAP | Non-CAD |  | QLY.QAP | Quality | Quality Assurance Plan
QMP | Non-CAD |  | QLY.QMP | Quality | Quality Management Plan, & Quality Plan
|  | LOG |  | Logistics
LOP | Non-CAD |  | LOG.LOP |  | Logistics Plan
VCP | Non-CAD |  | LOG.VCP |  | Vehicle Control Plan
WST | Non-CAD |  | LOG.WST |  | Work Sites Traffic Control Plan
RTC | Non-CAD |  | LOG.RTC |  | Road Transport Contingency Plan
|  | MIS |  | Miscellaneous
HTT | Non-CAD |  | MIS.HTT |  | Hard Transmittal

## Crossrail (hidden)
MDL Description
Yes | Project Execution Plan
Yes | BIM Execution Plan | Sugg
Yes | Task/Master Information Delivery Plan | Sugg
Yes | Employer`s Information Requirements | Sugg
Yes | Standard Methods and Procedures | Sugg
Yes | Cad Standard | Sugg
Yes | Master Information Production and Delivery Table | Sugg
Add other BIM/CAD related and update Column E
Yes | Contract Document at Award | Sugg
Yes | Organisation Chart | Sugg
| Schedule of Deliverable Records and Contractor records (incl. design) | Sugg
Yes | Competency Management Plan | Sugg
Yes | Competency Matrix | Sugg
Training Programme
Yes | Labour & Equipment Records | Sugg
Yes | Procedure for Management and Mitigation for unforeseen events | Sugg
Yes | Commitment Compliance Plan (compliance with undertakings and assurances required under the Contract) | Sugg
Yes | Utilities Plan | Sugg
| Certificates of competency for personnel performing work affecting conformity to requirements | Sugg
| Infrastructure Manager Asset Register | Sugg
| Reports of Failures and Faults | Sugg
Yes | Listing/Reports of Key Performance Indicators | Sugg
Yes | Consents Management Plan | Sugg
| Resource Loaded Programme | Sugg
| Commissioning & Startup Programme | Sugg
Fair Payment Performance Report
| Accounts Administration Plan | Sugg
| Risk Management Plan | Sugg
| Contractor Document Control Distribution Matrix | Sugg
| Automation Plan | Sugg
Yes | Permission to Mobilise Certificate
Yes | Permission to Mobilise Check List
Yes | Site Start Work Check List
Yes | Pre-start Construction Check List
Yes | Schedule of subcontractors and suppliers
Yes | Works Contract Take Over Certificate
Yes | Works Contract Completion Certificate
Yes | List of Critical Construction Starts
Yes | Project Controls Plan | Sugg
Yes | Project Control Procedures +90 days | Sugg
| Cost Control Reports (Plant & Materials, Equipment and subcontractor procurement sheets) | Sugg
Programme/Schedule Reports
Yes | Critical Items Action Report (CIAR)
Yes | Cost /Value Reports
Trend Program
Trend Register
Yes | Monthly Progress Report
Yes | Weekly Progress Report
Yes | Daily Reports
Yes | Minutes of Meetings
Yes | Procurement Plan
Yes | Supplier Diversity Plan
Yes | Procurement Schedule
Equality and Diversity Strategic Plan
Diversity Training Plan
Strategic Labour Needs and Training (SLNT) Plan
Responsible Procurement Formal Response to RP Contract Deliverables
Yes | Quarterly RP Progress Report
Yes | Construction Phase Plan (WI Part 19 Health and Safety Management)
Yes | Health and Safety Plans | Avai
Yes | Health and Safety File | Avai
Brief Description of the Works
Residual Hazards
Design Criteria
Special Arrangements for Decommissioning / Demolition
Special Arrangement/Equipment for Cleaning and Maintenance
Location of Utilities and Services
H&S As-Built Drawing Register
Health and Safety Records
Yes | Health and Safety Reports
Yes | Contract Security Plan
Yes | Emergency Preparedness - Incident & Action Plans
Working Permits
Product Safety Data Sheets
Health and Safety Audit reports
Yes | Monthly Safety Review Meetings
Yes | Engineering Safety Management Plan
Yes | Engineering Safety Risk Assessment
Yes | Engineering Safety Justifications
Contractors (Project) Quality Plan
Assurance Plan
Quality System Procedures
Yes | Inspection Release Notes
Yes | Audit Schedules
Yes | Non-conformance Reports
Yes | Quality Audit Reports
Yes | Inspection & Test Records
Yes | Planned Surveillance Schedule
Yes | Surveillance Sheet/Reports
Environmental Plan
Environmental Management Plans
Environmental Monitoring Records
Environmental Consents (Section 61 / Schedule 17)
Environmental audit reports
Yes | Site Waste Management Plan
Yes | Design Package Execution Plan
Yes | Design Management Plan
Yes | Design Verification & Validation Plan
Yes | Design and Checking Procedures
Requirements Management Plan
Yes | System Requirement Specification
Assumptions Register, relevant to the Design Package, including specific technical assumptions
Human Factors Engineering Plan (HFEP)
Yes | RAM Management Plan | Avai
Yes | RAM Assessments
Yes | Electromagnetic Compatibility Management (EMC) Control Plan
Validation Test Plans
Validation Test Specifications
Validation Test Reports
Yes | Interface Management Plan
Yes | Interface Control Documents (ICDs)
Yes | Safety Risk Assessment Log
Yes | Designer’s CDM Risk Register
Yes | Health and Safety Management Plan
Yes | Comparative Safety Related Risk Assessments
Environmental Design Statement Checklist
Yes | Environmental and traffic surveys (Detailed scopes, method statements, risk assessments and other requirements statements)
Yes | Traffic Management Plan
Yes | Design Certificates
Civils - Non Contract
Civils - Contract
Mapping
Planning and Consents / Community Relations / Legal
Structures
Open
Environment
Stations Architecture
Stations Civil / Transportation
Yes | Stations Building Services
Stations Structures
Track Team
Systemwide
Power Supply
Railway Utilities
Geotechnical
Cut and Cover Tunnels
Retained Cuttings
Existing Utilities
Proposed Utilities Design
Private Company Utilities
Existing Third Party Drawings
Yes | Design Check Certificates
Yes | Design Completion Certificate (DCC)
Integration and Compliance Certificate
Yes | As Built Design Compliance Certificate
Progress Reports
Data Sheets
Schedules and Records
Surveys Schedules
Accomodation Schedules
Ceiling Finishes Schedules
Door Schedules
Window Schedules
Ironmongery Schedules
Sanitary Schedules
Fitting Fixtures Schedules
Landscape Schedules
Yes | Signage Schedules
Yes | Equipment Schedules
Schedule of Builder's Work
Structural Concrete Elements: Bending Schedules
Electrical Load Schedules
Distribution Board Schedules
Testing and Commissioning Strategy
Maintenance Manual
Works Package Plans
Asset Management Plan
Material Approvals
Design Programme
Specifications
Design Calculations
Design Statements
Drawings (Civil, Architecture, M&E, Building, Communication)
3D Models
Earthing & Bonding Schedules & Layout Drawings
Electrical Layout Drawings
Lighting and Small Power Layouts
Equipment Data Sheets
Equipment Room Layout Drawings
Fire & Gas Detection Layout Drawings
General Piping & Routing Drawings
HVAC Ducting Layouts
Piping Isometrics
Pressure & Instrumentation Diagrams
Wiring Diagrams
Design Reports/Technical Reports
Surveys
Yes | Logistics Plan
Yes | Excavated Materials Plan
Yes | Sustainable Transport Plan
Yes | Modularisation & Off Site Assembly Plan
Lorry Driver Induction Training Plan
Vehicle & Driver Safety Plan
Consolidation Plan
Yes | Vehicle Control Plan
Daily Vehicle Movement Plan
Vehicle Security Plan
Yes | Work Sites Traffic Control Plan
Traffic Management System
Delivery Plan (Highways & Traffic)
Yes | Road Transport Contingency Plan
Yes | Schedule of Method Statements
Yes | Method statements
Yes | Schedule of Inspection and Test Plans
Inspection and Test Plans
Quantity Unit Rate Reports
Check prints of drawings, reports and calculations
Material Specifications and Catalogues
Yes | Bills of Materials/Quantity
Yes | Surface Preparation / Painting Specification
Painting/Coating Procedure
Approved Repair Procedure
Yes | Working Drawings
Yes | 3D Models
Hand-over outstanding works/defects list
Yes | Material Proposal Schedule
Yes | Material Compliance Record
Samples/Mock-ups/Test Panels and Benchmarking
Yes | Material & Product Certificates
Certification Record Packages
Certification Package Listing
Certification Package Review Statement
Yes | Sub construction & Construction Certificates
Yes | Whole Contract Construction Certificate
Dimensional Report
Factory acceptance test reports
Yes | Site acceptance test reports
Yes | Inspection release certificates
Building settlement/damage reports
Yes | Archaeological and historical building records
Yes | Structural settlement/damage reports/summaries
Revision X0 Red Line Marked Up Drawings
Geological / Ground Investigation Records
Yes | Earthworks Compaction Records
Yes | Piling Records
Embedded Walling Records
Yes | Pre and Post Concrete Pour Records
Temporary Works and Equipment Records relating to equipment left in the permanent works by agreement of the Project Manager
Yes | Ground Treatment Records
Inspection, Waterproofing Records and Reports
Specifications of installed Equipment
Vendor/Supplier Certification Documentation
Surveys
A drawing of the plan layout of the items of plant & materials
An integration file with calculation of gaps
Quality Control Certificates for aluminothermic welds with the positions shown on a schematic drawing
Dossier for switches and crossovers
Installation Plan including a list of plant
Quality Acceptance File including traceability with the as built and installation and the plans of work carried out
As-built records of rails laid with repairs identified on rail certificate (burns, repairs, damaged repairs) as a result of arc welding or rail removal
Distressing Certificates
Quality Control Certificates for aluminothermic welds
Records of each lifting pass
Track recordings by inspection cars
Track recordings by tamping machines
Building Heating/Ventilation & Air Conditioning records
Building Electrical System records
Building Water Distribution System records
Building Fire Protection & Control System records
Building Security System records
Building Audio/PAVA System records
Building Train Indicator System records
Building CCTV System records
Building Communication System records
Building Lifts & Escalator System records
Building Architectural Records
Building Radio control System records
Building Management System records
Yes | Maintenance Records – Plant & Equipment
Yes | Operational Manuals
Yes | Records of modifications made to the completed infrastructure or installed equipment
Yes | Recommended List of Spares
Yes | Training Strategy
Yes | Training Plan
Support Trainng Manuals
Yes | Installation Release Note - LV Power & Lighting System
Yes | Installation Release Note - HVAC
Yes | Installation Release note - Building Management System
Yes | Installation Release Note - Fire Detection/Protection System
Yes | Installation Release Note - Lifts
Yes | Installation Release Note - Escalators
Yes | Installation Prelease Note - UPS
Yes | Installation Release Note - Public Address System
Yes | Installation Release Note - CCTV/Security System
Yes | Installation Release Note - Train Display System
Yes | Installation Release Note - Help Points
Yes | Installation Release Note - Platform Passenger Doors
Yes | Installation Release Note - Radio System
Yes | Installation Release Note - Trace Heating & Heat Maintenance System
Yes | Installation Release Note - Water Distribution System
Yes | Installation Release Note - Smoke Detection System
Yes | Test and Commissioning Certificates
Yes | Test Plans and Test Reports

## Doc Group System (hidden)
Project & Programme Management
Project Controls
Health, Safety, Security and Environment
Quality
Design
Logistics
Construction Process
Procurement
Track Records
Building & Equipment
Operation and Maintenance
Test and Commissioning

## Dept. Team (hidden)
Viaduct | Station | Traction | Rolling Stock | Telecom | Depot | Signalling | Track | E&M
Tech. Spec. | Tech. Spec. | Tech. Spec. | Tech. Spec. | Tech. Spec. | Tech. Spec. | Tech. Spec. | Tech. Spec. | Tech. Spec.
Mayur | Anurag | Mandal | Upadhayaye | Kshitiz | Dixit | Snehalatha |  | Pankaj
Chandewar | Satsh |  | Shweta | Vinod Kumar | Sarang | Beura
RamNavas | RamNavas |  | Ravi